Subject: Corrective plan — stop-bill Maya / Whiptail and right-size Hare, Tonto, Ranger, Windmill now

I am writing you directly. SPS leadership has lost confidence in Jacobs project-execution staffing. Maya and Whiptail are off the Jacobs bench because of cost, not because the work disappeared. We will not recover that confidence with a 2027 lean-staffing study. We recover it by cutting unauthorized charges this week and running the four remaining jobs on a named, capped roster that can be audited against deliverables.

What leadership has already decided

Maya ISD moved to 2029. Whiptail ISD moved to 2030. Jacobs is directed to stop all billing on both projects as of 30 September 2026 and turn the files over to Company. On Whiptail alone, Jacobs has billed approximately $1.7 million — 7% of total project budget — before 30% design, and has billed materially more than Quanta, who is executing the work. That ratio is the problem.

These dollars are project-execution charges on capital projects. They are not Program, CPO, or BCG.

- Jacobs MPG support generally charges capital projects. That is not a defense.

- CPO is the exception: separate POs by OpCo across Tier 1 jobs.

- BCG support for the top 100 sits on a different PO.

- If the execution org chart labels a person “Portfolio support,” those hours are still hitting the capital project. That label does not make them program cost.

The question is simple: how many people are charging project execution, and what value did those hours produce?

SPS has heard that the model needs to get leaner. Meaningful reductions do not wait until 2027. If a person is not tied to defined, necessary work today, they come off the timesheet now. I am not aware of a contractual constraint that prevents that. If Jacobs believes one exists, put it in writing by Friday. If none exists, say none exists.

Authorized model on the four jobs that remain

Effective 1 October 2026, Hare, Tonto, Ranger, and Windmill may carry only these Jacobs functions:

| Seat | Rule |
| --- | --- |
| 1 PM | One named PM. Not a PM plus a deputy plus an engagement manager on the same WO. |
| 1 PMA | One coordinator. Artifacts and invoice packages, not standing meeting time. |
| Scheduler | One scheduler across the four jobs until construction density requires a written split. |
| Accounting | Company-controlled invoice test. Jacobs does not self-approve. |
| Owner’s engineering | Named reviewers only, tied to the next gate. No unassigned “support” engineers. |

Anything else requires a Company-signed surge form: name, classification, weekly hour cap, start, finish, and the file that exists when the surge ends. No form, no bill.

Maya and Whiptail after 30 September: one transition memo, a file index, and a final invoice for hours incurred on or before the stop-bill date. Not knowledge transfer, restart planning, or archive hygiene. A 2028 restart is a new roster, not the old one coming back on.

Answers leadership asked for — and what we will do instead of explaining the org chart

1. What is “Portfolio support” doing, and why is it on the capital project?
Jacobs will list, by 3 October, every person coded Portfolio support or equivalent on the six jobs for July–September 2026: name, classification, hours, WO / WBS, and the artifact produced. If the artifact does not exist, the hours are not payable. Portfolio support that cannot be tied to a live deliverable on Hare, Tonto, Ranger, or Windmill is removed from those WOs this week. We will not argue that a matrix label converts project cost into program cost.

2. Which resources are required for current scope, and what is the objective basis?
Required names are only the seats above, plus reviewers on a current package.

- Hare — 30% page turn 6 November 2026. Review hours tracked against an ~80-hour package budget. Live WBS only: DCP .001, Comms .002, Hendricks .005, TAM .006, TIF .008. Hendricks retirement does not charge until after ISD and a written start.

- Ranger and Windmill — still in the Oct–Dec 30% window. Same 80-hour cap. No invoice approved until each job has a one-pager: governing ISD, company equipment, WBS, land, AMD commercial. Windmill timesheets that resemble Whiptail are rejected.

- Tonto — already past 30%. Early 60% is allowed only with a separate hour cap. It does not get a second Jacobs crew and does not raid the other three WOs.

Objective basis is the next gate, the WBS, and the hour cap — not headcount on an engagement chart.

3. What prevents immediate reduction?
Company position: nothing that Jacobs has shown us. Onboarding lag is three to four weeks; adding people does not buy October or the Hare page turn. A 2027 scoping effort is not a constraint on today’s timesheets. If Jacobs has a contract clause, notice period, or demobilization cost that blocks a named person from coming off a WO in October, send the clause and the name by 3 October. Otherwise reductions start 1 October.

4. What reductions happen now, on what date — not in 2027?

| Date | Action | Accountable |
| --- | --- | --- |
| 30 Sep 2026 | Maya / Whiptail stop-bill. Codes closed. | Jacobs engagement lead + Company accounting |
| 1 Oct | Invoice hold. No payment until the eight-line test below passes. | Company accounting |
| 3 Oct | Named incumbents for PM, PMA, scheduler, OE on each live job. Vacant seat = $0. Full Jul–Sep charger list by person / hours / class / WO. Written ack that anyone not on the roster or a surge form is unauthorized. | Jacobs engagement lead |
| This week | Remove extra PMs, client managers, unassigned disciplines, and meeting-only names from the four WOs. Cancel Jacobs standing meetings that are not the Tuesday owner huddle or one working session per job. | Jacobs PM + PMA |
| 31 Oct | Look-back closed on Apr–Sep billings for all six jobs. Whiptail $1.7M / 7% tied to actual invoices. Questioned hours: 10 business days to prove value. Silence = credit memo. | Company accounting; Jacobs supplies backup |
| 6 Nov | Hare 30% run only with people on the authorized sign-in sheet. | Jacobs PM + OE |
| Nov–Dec | Ranger and Windmill 30% on the same roster and 80-hour cap. | Jacobs PM + OE |
| Dec invoice | First clean cycle: zero unauthorized names. | Jacobs PM + Company accounting |
| 15 Jan 2027 | Roster recertification before Tonto 60%. | PMA |

That is the reduction timeline. It does not wait for a 2027 effort.

5. Controls so remaining staff match workload and every charge shows value

Every Jacobs invoice from October forward must pass all eight tests. Fail the line, short-pay the line. Fail the roster, hold the invoice.

- Job is Hare, Tonto, Ranger, or Windmill.

- Person is on the authorized roster or a current surge form.

- Classification matches the work (PM hours are PM work, not design).

- Hours hit a live WO and a valid Exhibit G WBS. Accounting will not guess codes.

- Backup exists: date, hours, one-line description of the artifact. No backup in five business days = reject.

- Hours at or under the weekly cap on the roster.

- Meeting time only if the person was on the published agenda.

- No onboarding, unapproved travel, internal Jacobs coordination, or “transition.”

Labor curves stay quarantined until a schedule has a critical path to ISD. A curve is not permission to staff.

How Jacobs earns SPS trust back on the four jobs that are left

Trust is not a meeting. It is four visible results.

- Stop the bleeding in public. Written acknowledgement of the Maya / Whiptail stop-bill and the four-job roster, on your letterhead, by 3 October.

- Put names on seats and take names off WOs. One PM, one PMA, one scheduler, named OE. Publish who came off Hare, Tonto, Ranger, and Windmill this week.

- Pay only for files. Comment logs, one-pagers, P6 that includes the full WBS, studies Company directed. Hours without an artifact get credited, not explained.

- Hit the next gates without a surge cloud. Hare 6 November, then Ranger and Windmill 30%, without rebuilding the Whiptail bench. Tonto 60% does not become a fourth unofficial team.

If those four things happen, SPS can defend keeping Jacobs on the remaining work. If October still looks like Whiptail — more Jacobs cost than contractor progress, portfolio-support hours with no product, reductions parked in 2027 — leadership will not wait for another assessment.

I am not asking for a restatement of the current structure. I am asking you to confirm the stop-bill, name the five seats, remove everyone else, and run December’s invoice clean. Please reply with the 3 October package and the name of the single Jacobs executive who owns this recovery.